TWO-MONTH IMPLEMENTATION PLAN

AdaptiveOrchestrator: Dynamic Edge–Cloud Orchestration Framework

Full Pipeline Implementation, Testing & Documentation

Sensor Simulator  ·  Edge Orchestrator  ·  Kafka  ·  Spark Streaming  ·  Delta Lake  ·  SHAP  ·  MLflow

Candidate: Ajith Kumara   |   Supervisor: Dr. Thushari Silva   |   University of Moratuwa

# 1.  Executive Summary

This document is the complete project management and technical architecture plan for implementing AdaptiveOrchestrator over eight weeks. It covers every component, every test, every deliverable, and every daily task required to produce a fully working, tested, and documented pipeline by the end of Week 8.

| Dimension | Detail |
| --- | --- |
| Project name | AdaptiveOrchestrator — Dynamic Edge–Cloud Orchestration Framework |
| Total duration | 8 weeks (approximately 60 working days) |
| Environment | WSL2 Ubuntu 22.04 on Intel i5-1135G7, 16GB RAM, Docker Desktop 29.2 |
| Edge simulation | Docker container limited to 1 vCPU, 4GB RAM (Jetson Nano profile) |
| Network simulation | tc netem on Docker bridge interface (no physical hardware needed) |
| Dataset | CWRU Bearing + SKAB (synthetic replay during Week 1, real datasets from Week 2) |
| Cloud stack | Kafka + Spark 3.5 + Delta Lake + SHAP + MLflow — all running in Docker |
| Testing | Unit tests per component + integration tests + 5 formal evaluation scenarios |
| Documentation | README per component + API docs + thesis-ready results tables |
| Hard gates | 3 non-negotiable milestones — project stops until each is passed |

# 2.  Honest Scope Assessment

Two months for a full production-grade pipeline is extremely aggressive. The plan below is achievable but requires 4–6 focused hours per day, strict adherence to the simplification-first principle, and zero gold-plating. Every component is built to be correct and testable — not beautiful.

The raw component-by-component estimate is 50–70 developer-days. Spread across 60 calendar days at 4–6 hours per day, this is feasible with one critical architectural decision:

The Strangler Fig Principle — Applied Throughout This Plan - Weeks 1–5: Build with lightweight local equivalents (NATS, simple Parquet processor, local file storage). - Weeks 6–7: Replace with production components (Kafka, Spark Streaming, Delta Lake) using the same interfaces. - Week 8: Run formal evaluation on the production stack. - This approach ensures you always have a working system. You never spend a week with nothing running. - Kafka and Spark are powerful but complex to debug. Building on simple components first means bugs are in your code, not in Kafka configuration.

# 3.  Full Technology Stack

Every component in the system runs inside Docker on WSL2. No cloud accounts, no external services, no hardware purchases required. The entire pipeline is self-contained and reproducible from a single docker-compose up command.

| Layer | Component | Technology | Docker Image | Purpose |
| --- | --- | --- | --- | --- |
| Simulation | Sensor Simulator | Python 3.10 | python:3.10-slim | Replay CWRU/SKAB datasets at configurable Hz |
| Edge | Inference Engine | scikit-learn IF | python:3.10-slim | Local anomaly detection — no cloud dependency |
| Edge | Context Monitor | psutil + ping | python:3.10-slim | Measures latency, CPU, RAM every second |
| Edge | Policy Executor | Python asyncio | python:3.10-slim | Core innovation — runtime mode decisions |
| Edge | NATS Buffer | NATS JetStream | nats:latest | Local event queue during WAN outage |
| Edge | Alert Router | MQTT + FastAPI | python:3.10-slim | Multi-channel alerting during outage |
| Messaging | Kafka Broker | Apache Kafka | confluentinc/cp-kafka:7.5 | Event streaming edge → cloud |
| Messaging | Zookeeper | Apache Zookeeper | confluentinc/cp-zookeeper:7.5 | Kafka coordination |
| Cloud | Kafka Producer | confluent-kafka-python | python:3.10-slim | Bridges NATS events into Kafka topics |
| Cloud | Spark Streaming | Apache Spark 3.5 | bitnami/spark:3.5 | Stream processing of sensor events |
| Cloud | Delta Lake | Delta-Spark | bitnami/spark:3.5 | ACID-compliant lakehouse storage |
| Cloud | SHAP Explainer | SHAP + FastAPI | python:3.10-slim | Anomaly explanation for Hybrid mode |
| MLOps | MLflow | MLflow 2.x | ghcr.io/mlflow/mlflow | Model versioning and experiment tracking |
| Network Sim | tc netem | Linux kernel | WSL2 native | Latency/loss injection on Docker bridge |
| Monitoring | MQTT Broker | Mosquitto | eclipse-mosquitto | Local alert distribution on LAN |

# 4.  Project Folder Structure

This structure must be created on Day 1 and never deviated from. Every component lives in its own directory with its own __init__.py, making imports clean and tests isolated.

adaptive_orchestrator/ ├── components/ │ ├── sensor_simulator/ simulator.py, __init__.py │ ├── edge/ │ │ ├── inference_engine/ engine.py, trainer.py │ │ ├── context_monitor/ monitor.py │ │ ├── policy_executor/ executor.py │ │ ├── buffer/ nats_buffer.py │ │ └── alert_router/ router.py, dashboard.py │ └── cloud/ │ ├── kafka_producer/ producer.py, consumer.py │ ├── spark_processor/ streaming_job.py │ ├── delta_lake/ writer.py, reader.py │ ├── shap_explainer/ explainer.py, api.py │ └── mlflow_registry/ tracker.py ├── tests/ │ ├── unit/ test_*.py per component │ ├── integration/ test_pipeline_*.py │ └── evaluation/ scenario_*.py ├── scripts/ │ ├── scenarios/ scenario1_normal.sh ... scenario5_cost.sh │ └── parse_results.py ├── config/ │ └── settings.py single source of all thresholds ├── data/ CWRU + SKAB datasets ├── logs/ structured JSON logs ├── docs/ component READMEs ├── docker-compose.yml ├── requirements.txt └── setup.sh

# 5.  Master Schedule — 8-Week Gantt

The schedule is structured so that each week builds exactly one layer of the system. No week attempts to build across multiple layers simultaneously. This is the single most important rule for hitting the deadline.

| Component / Sprint | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environment & Scaffold | █ |  |  |  |  |  |  |  |
| Sensor Simulator | █ |  |  |  |  |  |  |  |
| Inference Engine (IF) | █ | █ |  |  |  |  |  |  |
| Context Monitor |  | █ |  |  |  |  |  |  |
| Threshold Sweep Tests |  | █ |  |  |  |  |  |  |
| Policy Executor (Core) |  |  | █ |  |  |  |  |  |
| NATS Buffer + Overflow |  |  | █ |  |  |  |  |  |
| Alert Router (MQTT+Dash) |  |  |  | █ |  |  |  |  |
| Kafka Producer/Consumer |  |  |  | █ | █ |  |  |  |
| Spark Streaming Processor |  |  |  |  | █ |  |  |  |
| Delta Lake (Parquet→Delta) |  |  |  |  | █ |  |  |  |
| SHAP Explainer |  |  |  |  |  | █ |  |  |
| MLflow Model Registry |  |  |  |  |  | █ |  |  |
| Integration + Soak Test |  |  |  |  |  | █ |  |  |
| tc netem Scenario Scripts |  |  |  |  |  |  | █ |  |
| Formal Evaluation (5 scen) |  |  |  |  |  |  | █ |  |
| Documentation + README |  |  |  |  |  |  | █ | █ |
| Thesis Figures + Tables |  |  |  |  |  |  |  | █ |

Schedule Logic - Weeks 1–2: Data layer. Sensor data flows through the system. Core ML works. Nothing else is attempted. - Week 3: Orchestration layer. The policy executor is the entire research contribution — it gets a full week alone. - Week 4: Resilience layer. Alerts and buffer complete the edge-autonomous operation story. - Week 5: Cloud layer (lightweight). End-to-end pipeline works using simple components. - Week 6: Validation. Integration tests and 30-minute soak test. Hard gate before production stack. - Week 7: Production swap + formal evaluation. Kafka, Spark, Delta Lake replace simple components. - Week 8: Evaluation completion, documentation, thesis figures.

# 6.  Week-by-Week Detailed Plan

## Week 1 — Foundation, Environment, Sensor Simulator

Goal: By Friday, sensor data is flowing from the simulator through NATS into a trained Isolation Forest model and producing predictions. The pipeline is alive.

| Day | Component | What to Build | Test / Deliverable | Hrs |
| --- | --- | --- | --- | --- |

## Week 2 — Context Monitor + Threshold Sweep

Goal: The system knows its own state. Context monitor measures latency and CPU every second. Threshold sweep experiment produces evidence-based values for 500ms and 80%.

| Day | Component | What to Build | Test / Deliverable | Hrs |
| --- | --- | --- | --- | --- |

## Week 3 — Policy Executor: The Core Innovation

Goal: The orchestrator makes correct mode decisions and transitions. EDGE_ONLY triggers within 5 seconds of latency injection. This week has no distractions — it is entirely focused on the research contribution.

| Day | Component | What to Build | Test / Deliverable | Hrs |
| --- | --- | --- | --- | --- |

## Week 4 — Alert Router + NATS Buffer

Goal: During a simulated outage, the system alerts operators via MQTT and dashboard AND stores events locally with zero data loss. Resilience is complete.

| Day | Component | What to Build | Test / Deliverable | Hrs |
| --- | --- | --- | --- | --- |

## Week 5 — Cloud Pipeline (Lightweight → Production)

Goal: Events flow end-to-end from edge through to stored results. Start with lightweight components (Day 1–3), then replace with Kafka + Spark + Delta Lake (Day 4–5). Same tests pass against both.

| Day | Component | What to Build | Test / Deliverable | Hrs |
| --- | --- | --- | --- | --- |

## Week 6 — SHAP Explainer + MLflow + Soak Test

Goal: Hybrid mode is complete. MLflow tracks every experiment. The 30-minute soak test passes all criteria. This is the hard gate — nothing moves to Week 7 until it passes.

| Day | Component | What to Build | Test / Deliverable | Hrs |
| --- | --- | --- | --- | --- |

## Week 7 — Formal Evaluation: All 5 Scenarios

Goal: Collect all thesis metrics. Run each scenario script, parse logs, compute F1, mode switch latency, buffer integrity, cost audit, autonomy percentage. Generate all result tables.

| Day | Component | What to Build | Test / Deliverable | Hrs |
| --- | --- | --- | --- | --- |

## Week 8 — Documentation, Figures, Thesis Preparation

Goal: Every component has a README. All thesis figures are generated. The repository is clean, reproducible, and presentable to Dr. Thushari.

| Day | Component | What to Build | Test / Deliverable | Hrs |
| --- | --- | --- | --- | --- |

# 7.  Complete Test Plan

Every component has both unit tests and integration tests. Unit tests verify the component in isolation using mocks. Integration tests verify the component in context with real NATS, real Docker networking, and real tc netem injection.

| Component | Unit Tests | Integration Tests | Pass Criteria |
| --- | --- | --- | --- |
| Sensor Simulator | Shape, anomaly ratio, noise injection, SKAB columns | NATS message delivery at 100Hz for 60s | F1 on synthetic data > 0.85; zero dropped events at 100Hz |
| Inference Engine | Score range, decision threshold, latency, train/predict | End-to-end CWRU replay → prediction pipeline | P99 latency < 50ms; F1 > 0.85 on held-out CWRU |
| Context Monitor | Latency parse, CPU measure, RAM measure, unreachable | Context snapshot delivery to NATS every 1s | Latency measurement within ±50ms of tc netem injected value |
| Policy Executor | Mode logic rules, transition events, routing decisions | Mode switch within 5s of tc netem latency injection | EDGE_ONLY triggered at >500ms; CLOUD at <200ms; zero missed transitions |
| NATS Buffer | Push/pop, overflow policy, critical event preservation | Buffer → flush → Delta Lake with 100% integrity | Zero critical events lost at any buffer fill level |
| Alert Router | MQTT publish, dashboard render, channel fallback | Alert fires on all channels within 3s of ANOMALY event | All channels fire during simulated WAN outage |
| Kafka Producer | Message serialisation, topic routing, error handling | NATS → Kafka bridge throughput at 1000 events/s | Zero message loss; P99 produce latency < 100ms |
| Spark Processor | Stream parsing, window aggregation, Delta write | Full pipeline: Kafka → Spark → Delta Lake | Events appear in Delta Lake within 5s of production |
| Delta Lake | Parquet write, ACID transaction, schema evolution | Concurrent writes from multiple Spark partitions | Zero data corruption; query returns 100% of written events |
| SHAP Explainer | TreeExplainer output shape, feature names, score range | Hybrid mode: anomaly event → SHAP result < 500ms | P95 explanation latency < 500ms; all features explained |
| MLflow | Experiment logging, model registration, artifact storage | Full training run logged with metrics and model artifact | Model retrievable by version; metrics match training output |
| Full Pipeline | N/A | 30-minute soak test across all 3 modes | Zero crashes; all mode transitions correct; zero data loss |

Testing Stack: pytest + pytest-asyncio for all tests. Run with: python3 -m pytest tests/ -v --tb=short. Target: 100% of components have passing tests before Week 7.

# 8.  Formal Evaluation Scenarios

The five evaluation scenarios directly map to the three failure modes identified in the literature review. Each scenario is fully scripted and reproducible. Results are parsed automatically into structured JSON for thesis tables.

| # | Scenario | Network Condition | tc netem Command | Metric Collected | Target |
| --- | --- | --- | --- | --- | --- |
| S1 | Normal Baseline | No degradation | None (remove all qdiscs) | F1, latency, throughput | F1 > 0.95 |
| S2 | The Blackout | 100% packet loss × 30min | loss 100% | Edge autonomy %, buffer fill, recovery time | Autonomy > 99% |
| S3 | Satellite Link | 900ms ±150ms, 1.5% loss × 10min | delay 900ms 150ms loss 1.5% | Mode switch latency, F1 during degradation | Switch < 5s; F1 > 0.85 |
| S4 | CPU Storm | 90% CPU load × 10min | stress-ng --cpu 7 (7 of 8 cores) | Load-shed trigger, inference latency under load | Shed triggers at 80%; P99 < 100ms |
| S5 | Cost Audit | Varying criticality (10%→50% anomaly rate) | None — vary dataset injection rate | Cloud egress events vs static baseline | 40% reduction vs static |

# 9.  Risk Register and Mitigations

Ten risks were identified in the initial feasibility analysis. The table below shows the mitigation action and the week in which it is addressed. Risks marked with Architecture or Thesis require no code — only scoping decisions or thesis language.

| # | Risk | Action | When |
| --- | --- | --- | --- |
| R1 | Jetson compute overload | Resolved — Docker resource limits simulate constraints | Sprint 0 ✅ |
| R2 | Model drift during long outage | Scope 99% claim to <60min outages in thesis methodology | Week 6 |
| R3 | AWS cost spiral | All components run locally in Docker — zero cloud spend | Architecture ✅ |
| R4 | SHAP latency too slow | Benchmark TreeExplainer early — fallback to feature importance | Week 6 |
| R5 | Fixed thresholds arbitrary | Threshold sweep experiment produces evidence-based values | Week 2 |
| R6 | Dataset scope too narrow | Acknowledge CWRU+SKAB as benchmarks; synthetic multi-sensor | Week 1 |
| R7 | NATS buffer overflow | Buffer overflow test with drop-low-severity policy | Week 4 |
| R8 | Docker overhead distorts latency | Disclose in thesis; run --network host where possible | Week 7 |
| R9 | tc netem burst loss unrealistic | Use Markov state model; acknowledge limitation | Week 1 |
| R10 | MLOps out of M.Sc. scope | Manual retraining trigger; automate as future work | Week 6 |

# 10.  Hard Gates and Daily Rules

Three Hard Gates — Do Not Cross Without Passing - GATE 1 — End of Week 1: Sensor data flows through NATS into Inference Engine. F1 > 0.85 on synthetic CWRU data. If not — fix simulator or model before writing any orchestration code. - GATE 2 — End of Week 3: Policy Executor switches modes correctly. tc netem latency injection causes EDGE_ONLY within 5 seconds. Verified by integration test. If not — do not build cloud pipeline. - GATE 3 — End of Week 6: Full 30-minute soak test passes all criteria. Zero crashes. Zero data loss. All mode transitions correct. If not — fix before running formal evaluation. A failed soak in Week 7 is a crisis.

Non-Negotiable Daily Rules (Project Manager Mandate) - RULE 1 — Test before you move on. Never start the next component until the current one has a passing unit test. One untested component breaks three downstream. - RULE 2 — Commit every day. End of every working session: git add . && git commit -m 'Day X: [what completed]'. If it is not committed, it does not exist. - RULE 3 — If a component takes more than 2 days longer than planned, simplify it. A working simple version beats a broken complex one every time. - RULE 4 — Week 6 soak test is a hard gate. Do not start formal evaluation on an unstable system. Fix first, evaluate second. - RULE 5 — Never debug two components simultaneously. Isolate failures to one component before touching another. - RULE 6 — Log everything. Every component writes structured JSON logs. You cannot evaluate what you cannot measure.

# 11.  Definition of Done

The project is complete when all of the following are true simultaneously. Not when some are true. All of them.

| # | Criterion | How Verified |
| --- | --- | --- |
| 1 | All 11 component unit test suites pass with zero failures | python3 -m pytest tests/unit/ -v shows all green |
| 2 | Full pipeline integration test passes for 30 consecutive minutes | soak_test.sh completes with all criteria met |
| 3 | All 5 evaluation scenarios produce recorded results | logs/s1_results.json through s5_results.json all exist and are parseable |
| 4 | F1 score above 0.90 under normal conditions | parse_evaluation_results.py shows F1 column > 0.90 for S1 |
| 5 | Edge autonomy above 99% during 30-minute outage | S2 results show autonomy_pct > 99 |
| 6 | Mode switch latency below 5 seconds | S3 results show mode_switch_latency_s < 5 |
| 7 | Zero data loss across all scenarios | Buffer flush integrity = 100% in all scenario logs |
| 8 | Cloud cost reduction above 40% vs static baseline | S5 results show cost_reduction_pct > 40 |
| 9 | All 11 component READMEs written and accurate | docs/ directory contains 11 README files, each with working example |
| 10 | Fresh clone + README instructions produces working system | Day 5 Week 8 verification passes from /tmp clean clone |

This plan is aggressive but achievable.

The difference between finishing and not finishing is one rule:

Do not move to the next component until the current one is tested and committed.

AdaptiveOrchestrator   |   Ajith Kumara   |   University of Moratuwa   |   2026